## Risk Assessment
PDE3823 Risk Assessment - Digital Twin-Enabled AI Fault Detection for Thrust Reversers
Project Owner: | Mihir Ragoonauth
Student ID: | M00955111
Submission Advisor: | Mehnaz Hamilton
Date: | 2026-04-01
TASK / ACTIVITY | HAZARD | WHO MIGHT BE HARMED | RISK LIKELIHOOD | RISK SEVERITY | RISK LEVEL | CONTROL MEASURES PUT IN PLACE TO REDUCE RISK | NEW RISK LIKELIHOOD | NEW RISK SEVERITY | CONTROLLED RISK LEVEL
Importing and modifying purchased Trent 900 CAD model in Siemens NX | File format incompatibility, geometry errors or missing thrust reverser components | Student (project delays) | Possible (3) | Minor Setback (2) | 6 | Purchased model early to verify compatibility; obtained STEP assembly files from creator; only need to add thrust reverser components to existing geometry | Very Unlikely (1) | Minor Setback (2) | 2
Running MCD physics simulation for thrust reverser deployment | Simulation fails to converge due to improper constraints or conflicting joint definitions | Student (project delays) | Possible (3) | Minor Setback (2) | 6 | Started with simplified physics model; transitioned to analog-only control architecture on advisor recommendation; validated against known deployment times | Unlikely (2) | Minor Setback (2) | 4
Generating labelled deployment scenarios for Random Forest training | Insufficient data diversity resulting in poor classifier generalisation | Student (project outcomes); future users of the fault detection system | Possible (3) | Moderate Delay (3) | 9 | Automated batch recording system expanded from 250 to 1,400 scenarios; randomised parameters within defined ranges; dataset covers 7 fault classes; XGBoost classifier selected after evaluating Random Forest, SVM and Decision Trees | Very Unlikely (1) | Minor Setback (2) | 2
Training and validating Random Forest classifier | Classifier fails to achieve 90% accuracy target | Student (project outcomes) | Possible (3) | Moderate Delay (3) | 9 | Multiple algorithms evaluated (Random Forest, XGBoost, SVM); XGBoost selected after systematic comparison; 1,400 scenarios across 7 fault classes; 10-run robustness testing confirms 99.8% accuracy | Unlikely (2) | Minor Setback (2) | 4
Validating digital twin accuracy against real-world thrust reverser behaviour | Incorrect assumptions produce misleading simulation outputs | Student (project credibility); anyone relying on simulation results | Possible (3) | Moderate Delay (3) | 9 | Deployment timing validated against published specifications; sensor data patterns validated against expected behaviour; limitations clearly documented in report | Unlikely (2) | Minor Setback (2) | 4
Using Siemens NX, TIA Portal and PLCSim Advanced for development | Loss of software license access or laptop hardware failure | Student (project delays) | Unlikely (2) | Major Setback (4) | 8 | University license access verified; regular backups to OneDrive and external drive; university lab computers available as backup | Very Unlikely (1) | Moderate Delay (3) | 3
Managing 12-week project schedule across multiple technical domains | Accumulated delays jeopardise final deliverables | Student (grade and project completion) | Possible (3) | Major Setback (4) | 12 | Pre-purchased CAD model saves 2-3 weeks; weekly progress tracking against Gantt chart; minimum viable deliverables defined; 5-week buffer | Unlikely (2) | Minor Setback (2) | 4
CAD modeling, PLC programming and Python development sessions | Eye strain, back pain or repetitive strain injury from prolonged screen time | Student (health) | Possible (3) | Minor Setback (2) | 6 | Follow 20-20-20 rule; maintain proper posture and workstation ergonomics; regular breaks; limit daily screen time to 6-8 hours | Unlikely (2) | Near Miss (1) | 2
Using purchased CAD model and referencing external resources | Improper use or attribution violates license terms | Student (academic integrity); original CAD model creator | Unlikely (2) | Minor Setback (2) | 4 | License terms reviewed (educational use permitted); original creator properly attributed; thrust reverser components are 100% original work | Very Unlikely (1) | Near Miss (1) | 1
Handling simulation data for ML training | Data handling issues or ethical concerns | N/A (all data is synthetic, computer-generated) | Very Unlikely (1) | Near Miss (1) | 1 | All data is synthetic; no human participants or personal data; publicly available specifications used; standard university approval | Very Unlikely (1) | Near Miss (1) | 1
Wiring and commissioning the Festo EduTrainer pneumatic station with S7-1200 PLC | Incorrect wiring causing solenoid valve damage, short circuits, or PLC output module failure | Student (project delays); equipment damage | Possible (3) | Moderate Delay (3) | 9 | I/O addresses verified in TIA Portal tag table before energising; each actuator tested individually with simple deploy/retract code before running full state machine; all wiring checked against handover document | Unlikely (2) | Minor Setback (2) | 4
Operating pneumatic rotary actuators under compressed air supply | Sudden actuator movement causing pinch or crush injury to hands or fingers | Student (physical injury); anyone near the station | Possible (3) | Major Setback (4) | 12 | Hands kept clear of actuators during operation; air supply isolated before any mechanical adjustments; flow restrictors fitted to reduce stroke speed; PLC controls all movement with no manual override required during testing | Unlikely (2) | Minor Setback (2) | 4
Adjusting flow restrictors and repositioning magnetic sensors on rotary actuators | Air supply active during adjustment causing unexpected actuator movement; sensor misalignment causing unreliable position detection | Student (physical injury; project delays) | Possible (3) | Moderate Delay (3) | 9 | Air supply isolated and PLC set to STOP before any physical adjustment; sensor positions validated by checking tag table monitor values in TIA Portal after each adjustment; flow restrictor settings bench-tuned incrementally | Very Unlikely (1) | Minor Setback (2) | 2
Working with compressed air system and pneumatic tubing connections | Disconnected tubing causing pressurised air release; noise exposure from pneumatic exhaust | Student (minor injury from air blast; hearing discomfort) | Unlikely (2) | Minor Setback (2) | 4 | All tubing connections checked before pressurising; air supply pressure regulated to operating range; station operated in ventilated lab environment; ear protection available if prolonged testing required | Very Unlikely (1) | Near Miss (1) | 1
Using borrowed WorldSkills pneumatic equipment (rotary actuators, valves, check valves) | Damage to or loss of loaned equipment; inability to return equipment in working condition | Student (professional relationship); Mehmet Karamanoglu (equipment owner) | Unlikely (2) | Moderate Delay (3) | 6 | Equipment inventory documented in handover notes; station operated only under supervised lab conditions; all components returned to original configuration after testing; any damage reported immediately | Very Unlikely (1) | Minor Setback (2) | 2
RISK LIKELIHOOD | RISK SEVERITY
Very Likely (5) | Project Failure (5)
Likely (4) | Major Setback (4)
Possible (3) | Moderate Delay (3)
Unlikely (2) | Minor Setback (2)
Very Unlikely (1) | Near Miss (1)
RISK LEVEL KEY:
High (9-25) | Medium (5-8) | Low (1-4)