## Risk Assessment
PDE3823 Risk Assessment - Digital Twin-Enabled AI Fault Detection for Thrust Reversers
Project Owner: | Mihir Ragoonauth
Student ID: | M00955111
Submission Advisor: | Mehnaz Hamilton
Date: | 12 February 2026
TASK / ACTIVITY | HAZARD | WHO MIGHT BE HARMED | RISK LIKELIHOOD | RISK SEVERITY | RISK LEVEL | CONTROL MEASURES PUT IN PLACE TO REDUCE RISK | NEW RISK LIKELIHOOD | NEW RISK SEVERITY | CONTROLLED RISK LEVEL
Importing and modifying purchased Trent 900 CAD model in Siemens NX | File format incompatibility, geometry errors, or missing thrust reverser components | Student (project delays) | Possible (3) | Minor Setback (2) | 6 | Purchased model early to verify compatibility; obtained STEP assembly files from creator; only need to add thrust reverser components to existing geometry | Very Unlikely (1) | Minor Setback (2) | 2
Running MCD physics simulation for thrust reverser deployment | Simulation fails to converge due to improper constraints or conflicting joint definitions | Student (project delays) | Possible (3) | Minor Setback (2) | 6 | Started with simplified physics model; transitioned to analog-only control architecture on advisor recommendation; validated against known deployment times | Unlikely (2) | Minor Setback (2) | 4
Generating labelled deployment scenarios for Random Forest training | Insufficient data diversity resulting in poor classifier generalisation | Student (project outcomes); future users of the fault detection system | Possible (3) | Moderate Delay (3) | 9 | Automated batch recording system captures 250 scenarios; randomised parameters within defined ranges; data augmentation techniques available | Very Unlikely (1) | Minor Setback (2) | 2
Training and validating Random Forest classifier | Classifier fails to achieve 90% accuracy target | Student (project outcomes) | Possible (3) | Moderate Delay (3) | 9 | Multiple algorithms available (Random Forest, SVM, Decision Trees); systematic hyperparameter tuning; rule-based baseline provides fallback | Unlikely (2) | Minor Setback (2) | 4
Validating digital twin accuracy against real-world thrust reverser behaviour | Incorrect assumptions produce misleading simulation outputs | Student (project credibility); anyone relying on simulation results | Possible (3) | Moderate Delay (3) | 9 | Deployment timing validated against published specifications; sensor data patterns validated against expected behaviour; limitations clearly documented in report | Unlikely (2) | Minor Setback (2) | 4
Using Siemens NX, TIA Portal, and PLCSim Advanced for development | Loss of software license access or laptop hardware failure | Student (project delays) | Unlikely (2) | Major Setback (4) | 8 | University license access verified; regular backups to OneDrive and external drive; university lab computers available as backup | Very Unlikely (1) | Moderate Delay (3) | 3
Managing 12-week project schedule across multiple technical domains | Accumulated delays jeopardise final deliverables | Student (grade and project completion) | Possible (3) | Major Setback (4) | 12 | Pre-purchased CAD model saves 2-3 weeks; weekly progress tracking against Gantt chart; minimum viable deliverables defined; 5-week buffer | Unlikely (2) | Minor Setback (2) | 4
CAD modeling, PLC programming, and Python development sessions | Eye strain, back pain, or repetitive strain injury from prolonged screen time | Student (health) | Possible (3) | Minor Setback (2) | 6 | Follow 20-20-20 rule; maintain proper posture and workstation ergonomics; regular breaks; limit daily screen time to 6-8 hours | Unlikely (2) | Near Miss (1) | 2
Using purchased CAD model and referencing external resources | Improper use or attribution violates license terms | Student (academic integrity); original CAD model creator | Unlikely (2) | Minor Setback (2) | 4 | License terms reviewed (educational use permitted); original creator properly attributed; thrust reverser components are 100% original work | Very Unlikely (1) | Near Miss (1) | 1
Handling simulation data for ML training | Data handling issues or ethical concerns | N/A (all data is synthetic, computer-generated) | Very Unlikely (1) | Near Miss (1) | 1 | All data is synthetic; no human participants or personal data; publicly available specifications used; standard university approval | Very Unlikely (1) | Near Miss (1) | 1
RISK LIKELIHOOD | RISK SEVERITY
Very Likely (5) | Project Failure (5)
Likely (4) | Major Setback (4)
Possible (3) | Moderate Delay (3)
Unlikely (2) | Minor Setback (2)
Very Unlikely (1) | Near Miss (1)
RISK LEVEL KEY:
High (9-25) | Medium (5-8) | Low (1-4)